## COVER
K |  | KINGSFORM METALWORKS |  |  |  | DOCUMENT ID
KFR-002
|  | KINGSFORM ENGINEERING TOOLKIT |  |  |  | VERSION
V1.0
Project Documentation & Drawing Checklist
RFQ readiness and engineering drawing completeness review
ABOUT THIS WORKBOOK
Use this workbook before submitting an RFQ or releasing a drawing package. It checks whether the required documents are available, whether drawings contain the information needed for manufacturing, and whether engineering, purchasing and quality reviews have been completed.
WORKFLOW
01 | Complete PROJECT INFO |  |  | Identify the project, drawing standard, units, scope and responsible reviewer.
02 | Review REQUIRED DOCUMENTS |  |  | Confirm which files are required and whether the latest revisions are attached.
03 | Complete DRAWING REVIEW |  |  | Check identification, dimensions, tolerances, manufacturing, assembly and quality information.
04 | Resolve ACTION REPORT |  |  | Assign owners and target dates for missing or unclear information.
05 | Complete REVIEW RECORD |  |  | Obtain the required departmental approvals before releasing the package.
READINESS PRINCIPLES
REQUIRED |  | Items necessary to quote or manufacture the project must be confirmed or attached.
APPLICABLE |  | Conditional items should be activated only when relevant to the part or assembly.
CRITICAL |  | Missing critical information prevents reliable quotation or manufacturing release.
TRACEABLE |  | Drawing numbers, part numbers and revisions must be consistent across all files.
DOCUMENT CONTROL
Document ID |  | KFR-002 |  |  | Version | 1.0
Release Date |  | 2026-07-16 |  |  | Status | Released
Document Owner |  | KingsForm Engineering |  |  | Contact | info@kingsformmetalworks.com
This checklist does not replace formal design verification, customer approval or manufacturing engineering review. Dimensions, tolerances, material specifications and acceptance criteria remain subject to the released drawing package.
KingsForm Engineering Toolkit |  |  | KFR-002 ¦ Version 1.0 |  |  | www.kingsformmetalworks.com

## DASHBOARD
RFQ READINESS DASHBOARD | [7 empty] | KFR-002
Version 1.0
Resolve red items and review amber items before releasing the package for quotation or manufacturing.
OVERALL DOCUMENTATION READINESS | [5 empty] | RELEASE STATUS
0% | [5 empty] | INCOMPLETE
READINESS BY SECTION | [6 empty] | KEY RISK METRICS
Section | Weight | Completion | Status | Open Items | Required Action
Project Information | 15% | 0% | Incomplete | 14 | Complete required project identification and review-scope fields. |  | OPEN DOCUMENTS
Required Documents | 30% | 0% | Incomplete | 2 | Attach required files and confirm latest revisions. |  | 2
Drawing Review | 45% | 0% | Incomplete | 16 | Confirm drawing completeness and resolve critical open checks.
Review & Approval | 10% | 0% | Incomplete | 2 | Complete required departmental approvals. |  | CRITICAL DOCUMENTS OPEN
2
OPEN DRAWING CHECKS
16
CRITICAL DRAWING CHECKS
10
OPEN APPROVALS
2
FINAL RELEASE CHECK
Project information complete | [7 empty] | ACTION REQUIRED
No open required documents | [7 empty] | ACTION REQUIRED
No critical document gaps | [7 empty] | ACTION REQUIRED
No critical drawing-review gaps | [7 empty] | ACTION REQUIRED
No open required approvals | [7 empty] | ACTION REQUIRED
Overall readiness at least 90% | [7 empty] | ACTION REQUIRED
A high completion percentage does not override critical gaps. The package should not be released while any critical document, drawing or approval item remains open.
KingsForm Engineering Toolkit |  |  | KFR-002 ¦ Version 1.0 | [5 empty] | www.kingsformmetalworks.com

## PROJECT INFO
PROJECT DOCUMENTATION & DRAWING CHECKLIST |  |  | KFR-002
Version 1.0
Complete all yellow fields that apply. Required fields are marked with an asterisk (*).
1. CUSTOMER & PROJECT IDENTIFICATION
Company Name* |  | Contact Person*
Email* |  | Phone / WhatsApp
Project Name* |  | Customer RFQ No.
Primary Part / Assembly No.* |  | Drawing Revision*
Project Stage* |  | Review Date*
Project Description
2. DRAWING PACKAGE BASIS
Package Scope* |  | Drawing Standard
Primary Units* |  | Language
2D Drawing Format* |  | 3D Model Format
Latest Revision Confirmed* |  | Obsolete Files Removed
Part Numbers Consistent |  | Revision Codes Consistent
Assembly / BOM Applicable |  | Reference Sample Available
Customer Standard / Manual |  | NDA / Confidentiality
3. REVIEW RESPONSIBILITY & SCOPE
Lead Reviewer* |  | Lead Department*
Engineering Review Required |  | Purchasing Review Required
Quality Review Required |  | Production Review Required
Customer Approval Required |  | Management Approval Required
Planned RFQ / Release Date |  | Target Closure Date
Shared Folder / PLM Link
4. PROJECT-SPECIFIC NOTES
Known Risks / Open Questions
Special Manufacturing Assumptions
Additional Notes
PROJECT INFO COMPLETION |  | STATUS
0% |  | INCOMPLETE
KingsForm Engineering Toolkit | KFR-002 ¦ Version 1.0 |  | www.kingsformmetalworks.com

## REQUIRED DOCUMENTS
REQUIRED DOCUMENTS CHECKLIST | [7 empty] | KFR-002
Version 1.0
Set each file as Required, If applicable or Not required. A document is ready when it is attached or intentionally marked Not required.
TOTAL DOCUMENTS |  | REQUIRED / ACTIVE |  | READY |  | OPEN ITEMS |  | CRITICAL OPEN |  | COMPLETION
18 |  | 2 |  | 0 |  | 2 |  | 2 |  | 0%
No. | Document / File | Requirement | Status | Revision | File Type | File Name / Link | Owner | Readiness | Criticality | Target Date | Notes
1 | 2D part drawing | Required | Will send later |  | PDF |  | Customer Engineering | Open | Critical |  | Released drawing with dimensions, material, finish and revision.
2 | 3D model | If applicable | Not required |  | STEP / STP |  | Customer Engineering | Ready | Standard |  | Recommended for complex geometry and assemblies.
3 | DXF / profile / flat pattern | If applicable | Not required |  | DXF |  | Customer Engineering | Ready | Standard |  | Required for laser-cut profiles when available.
4 | Assembly drawing | If applicable | Not required |  | PDF |  | Customer Engineering | Ready | Critical |  | Show orientation, interfaces and item references.
5 | Bill of materials (BOM) | If applicable | Not required |  | XLSX / XLS |  | Customer Engineering | Ready | Critical |  | Use consistent item numbers and revisions.
6 | Exploded view / assembly sequence | If applicable | Not required |  | PDF |  | Customer Engineering | Ready | Standard |  | Useful for multi-part or serviceable assemblies.
7 | Welding drawing / weld map | If applicable | Not required |  | PDF |  | Customer Engineering | Ready | Critical |  | Specify weld type, size, length and acceptance criteria.
8 | Material specification | Required | Will send later |  | PDF |  | Customer Engineering | Open | Critical |  | Identify grade, standard, condition and certificate requirement.
9 | Surface finish specification | If applicable | Not required |  | PDF |  | Customer Engineering | Ready | Standard |  | Include process, color, gloss, texture and coating thickness.
10 | Heat treatment / hardness specification | If applicable | Not required |  | PDF |  | Customer Engineering | Ready | Standard |  | Include condition, hardness range and verification method.
11 | Inspection standard / quality plan | If applicable | Not required |  | PDF |  | Customer Quality | Ready | Critical |  | Mark CTQ items, sampling and reporting requirements.
12 | Approved sample / appearance standard | If applicable | Not required |  | Image |  | Customer Quality | Ready | Standard |  | Recommended for cosmetic surfaces and color matching.
13 | Functional / load test specification | If applicable | Not required |  | PDF |  | Customer Engineering | Ready | Critical |  | Define load, cycle, leakage, torque or other acceptance limits.
14 | Packaging specification | If applicable | Not required |  | PDF |  | Customer Purchasing | Ready | Standard |  | Include individual protection, labels and pallet requirements.
15 | Customer supplier quality manual | If applicable | Not required |  | PDF |  | Customer Quality | Ready | Standard |  | Include PPAP, traceability, retention and change-control rules.
16 | Customer logistics / labeling standard | If applicable | Not required |  | PDF |  | Customer Purchasing | Ready | Advisory |  | Include barcode, shipping mark and delivery requirements.
17 | NDA / confidentiality agreement | If applicable | Not required |  | PDF |  | Project Manager | Ready | Advisory |  | Confirm before sharing restricted technical files.
18 | Reference quotation / legacy supplier notes | If applicable | Not required |  | Other |  | Customer Purchasing | Ready | Advisory |  | Optional commercial or historical context.
KingsForm Engineering Toolkit |  |  | KFR-002 ¦ Version 1.0 | [5 empty] | www.kingsformmetalworks.com

## DRAWING REVIEW
DRAWING COMPLETENESS REVIEW | [7 empty] | KFR-002
Version 1.0
Review the latest released drawing package. Use Not applicable only where the feature or requirement genuinely does not apply.
TOTAL CHECKS |  | ACTIVE CHECKS |  | CONFIRMED |  | OPEN ITEMS |  | CRITICAL OPEN |  | WEIGHTED SCORE
51 |  | 16 |  | 0 |  | 16 |  | 10 |  | 0%
No. | Category | Drawing Check Item | Requirement | Review Status | Criticality | Drawing / File Reference | Readiness | Weight | Earned | Owner / Action | Notes
1 | Identification | Part number is shown and matches the file name / BOM | Required | Not reviewed | Critical |  | Open | 2 | 0
2 | Identification | Drawing number or document number is shown | Required | Not reviewed | Critical |  | Open | 2 | 0
3 | Identification | Drawing title / part description is clear | Required | Not reviewed | Standard |  | Open | 1 | 0
4 | Identification | Revision code and revision date are shown | Required | Not reviewed | Critical |  | Open | 2 | 0
5 | Identification | Units are identified | Required | Not reviewed | Critical |  | Open | 2 | 0
6 | Identification | Scale is identified or marked NTS | Required | Not reviewed | Standard |  | Open | 1 | 0
7 | Identification | Sheet number and total sheet count are shown | If applicable | Not applicable | Advisory |  | Ready | 0 | 0
8 | Identification | Drawing approval / release status is shown | Required | Not reviewed | Standard |  | Open | 1 | 0
9 | Material & Finish | Material grade and applicable standard are specified | Required | Not reviewed | Critical |  | Open | 2 | 0
10 | Material & Finish | Raw material form is clear: sheet, plate, tube, bar, casting, etc. | Required | Not reviewed | Standard |  | Open | 1 | 0
11 | Material & Finish | Sheet thickness / tube wall / stock size is specified | Required | Not reviewed | Critical |  | Open | 2 | 0
12 | Material & Finish | Material condition or temper is specified where relevant | If applicable | Not applicable | Standard |  | Ready | 0 | 0
13 | Material & Finish | Heat treatment and hardness requirements are specified | If applicable | Not applicable | Standard |  | Ready | 0 | 0
14 | Material & Finish | Surface finish process is specified | If applicable | Not applicable | Standard |  | Ready | 0 | 0
15 | Material & Finish | Color, gloss and texture requirements are specified | If applicable | Not applicable | Standard |  | Ready | 0 | 0
16 | Material & Finish | Coating thickness / corrosion performance is specified | If applicable | Not applicable | Standard |  | Ready | 0 | 0
17 | Dimensions & Geometry | Overall length, width and height are fully defined | Required | Not reviewed | Critical |  | Open | 2 | 0
18 | Dimensions & Geometry | Datum origin or dimensional reference is clear | Required | Not reviewed | Critical |  | Open | 2 | 0
19 | Dimensions & Geometry | Hole diameters and slot dimensions are defined | If applicable | Not applicable | Critical |  | Ready | 0 | 0
20 | Dimensions & Geometry | Hole / slot positions are fully located | If applicable | Not applicable | Critical |  | Ready | 0 | 0
21 | Dimensions & Geometry | Thread standard, size, pitch and depth are defined | If applicable | Not applicable | Critical |  | Ready | 0 | 0
22 | Dimensions & Geometry | Countersink / counterbore geometry is defined | If applicable | Not applicable | Standard |  | Ready | 0 | 0
23 | Dimensions & Geometry | Bend angles, inside radii and bend direction are defined | If applicable | Not applicable | Critical |  | Ready | 0 | 0
24 | Dimensions & Geometry | Tube diameter / section size and centerline geometry are defined | If applicable | Not applicable | Critical |  | Ready | 0 | 0
25 | Dimensions & Geometry | Cut length and end preparation are defined | If applicable | Not applicable | Standard |  | Ready | 0 | 0
26 | Dimensions & Geometry | Chamfers, edge radii and corner radii are defined | If applicable | Not applicable | Standard |  | Ready | 0 | 0
27 | Dimensions & Geometry | Orientation, symmetry and handedness are unambiguous | If applicable | Not applicable | Critical |  | Ready | 0 | 0
28 | Dimensions & Geometry | Reference dimensions are clearly identified | If applicable | Not applicable | Advisory |  | Ready | 0 | 0
29 | Tolerances & GD&T | General dimensional tolerance standard is stated | Required | Not reviewed | Critical |  | Open | 2 | 0
30 | Tolerances & GD&T | Critical dimensions have explicit tolerances | Required | Not reviewed | Critical |  | Open | 2 | 0
31 | Tolerances & GD&T | Datum reference frame is logical and manufacturable | If applicable | Not applicable | Critical |  | Ready | 0 | 0
32 | Tolerances & GD&T | GD&T symbols include datum references and modifiers | If applicable | Not applicable | Critical |  | Ready | 0 | 0
33 | Tolerances & GD&T | Flatness, straightness or profile controls are defined where needed | If applicable | Not applicable | Standard |  | Ready | 0 | 0
34 | Tolerances & GD&T | Surface roughness is specified for functional surfaces | If applicable | Not applicable | Standard |  | Ready | 0 | 0
35 | Tolerances & GD&T | Fits, clearances or interference classes are specified | If applicable | Not applicable | Critical |  | Ready | 0 | 0
36 | Tolerances & GD&T | Tolerance stack or functional interface has been reviewed | If applicable | Not applicable | Critical |  | Ready | 0 | 0
37 | Manufacturing & Welding | Intended manufacturing process is compatible with the drawing | Required | Not reviewed | Standard |  | Open | 1 | 0
38 | Manufacturing & Welding | Weld joint type, size, length and location are specified | If applicable | Not applicable | Critical |  | Ready | 0 | 0
39 | Manufacturing & Welding | Weld symbols and applicable welding standard are identified | If applicable | Not applicable | Critical |  | Ready | 0 | 0
40 | Manufacturing & Welding | Weld finish, grinding and cosmetic requirements are specified | If applicable | Not applicable | Standard |  | Ready | 0 | 0
41 | Manufacturing & Welding | Deburr and sharp-edge requirements are specified | Required | Not reviewed | Standard |  | Open | 1 | 0
42 | Manufacturing & Welding | Bend relief, corner relief or cutout rules are defined | If applicable | Not applicable | Standard |  | Ready | 0 | 0
43 | Manufacturing & Welding | Grain direction is specified where forming performance matters | If applicable | Not applicable | Advisory |  | Ready | 0 | 0
44 | Manufacturing & Welding | Machining allowance or post-weld machining is identified | If applicable | Not applicable | Standard |  | Ready | 0 | 0
45 | Manufacturing & Welding | Part marking and traceability requirements are specified | If applicable | Not applicable | Standard |  | Ready | 0 | 0
46 | Assembly & Interface | Assembly drawing and BOM are consistent | If applicable | Not applicable | Critical |  | Ready | 0 | 0
47 | Assembly & Interface | Mating surfaces and interface dimensions are fully defined | If applicable | Not applicable | Critical |  | Ready | 0 | 0
48 | Assembly & Interface | Fastener type, size, grade and quantity are specified | If applicable | Not applicable | Standard |  | Ready | 0 | 0
49 | Assembly & Interface | Torque, locking method or thread treatment is specified | If applicable | Not applicable | Standard |  | Ready | 0 | 0
50 | Assembly & Interface | Press-fit, insertion depth or locating features are defined | If applicable | Not applicable | Critical |  | Ready | 0 | 0
51 | Assembly & Interface | Clearance for motion, tools and assembly access is adequate | If applicable | Not applicable | Standard |  | Ready | 0 | 0
52 | Assembly & Interface | Assembly orientation and sequence are unambiguous | If applicable | Not applicable | Standard |  | Ready | 0 | 0
53 | Quality & Validation | Critical-to-quality characteristics are identified | Required | Not reviewed | Critical |  | Open | 2 | 0
54 | Quality & Validation | Inspection method or gauge requirement is defined for CTQ items | If applicable | Not applicable | Critical |  | Ready | 0 | 0
55 | Quality & Validation | Sampling, 100% inspection or FAI requirements are stated | If applicable | Not applicable | Standard |  | Ready | 0 | 0
56 | Quality & Validation | Material certificate / traceability requirement is stated | If applicable | Not applicable | Standard |  | Ready | 0 | 0
57 | Quality & Validation | Coating thickness, adhesion or corrosion test is defined | If applicable | Not applicable | Standard |  | Ready | 0 | 0
58 | Quality & Validation | Appearance acceptance standard or approved sample is available | If applicable | Not applicable | Standard |  | Ready | 0 | 0
59 | Quality & Validation | Functional, load, leakage, torque or cycle test is defined | If applicable | Not applicable | Critical |  | Ready | 0 | 0
60 | Packaging & Logistics | Individual protection and part-to-part separation are defined | If applicable | Not applicable | Standard |  | Ready | 0 | 0
61 | Packaging & Logistics | Label, barcode, part number and revision marking are defined | If applicable | Not applicable | Standard |  | Ready | 0 | 0
KingsForm Engineering Toolkit |  |  | KFR-002 ¦ Version 1.0 | [5 empty] | www.kingsformmetalworks.com

## ACTION REPORT
MISSING INFORMATION & ACTION REPORT | [5 empty] | KFR-002
Version 1.0
This sheet automatically lists unresolved drawing-review items by source row. Assign an owner, target date and closure note.
OPEN ITEMS |  | CRITICAL OPEN |  | DOCUMENTS OPEN |  | TOTAL ACTIONS |  | ACTION STATUS
16 |  | 10 |  | 2 |  | 18 |  | OPEN
Source Row | Category | Open Check Item | Criticality | Current Status | Owner | Target Date | Closure Status | Closure Note | Closed Date
11 | Identification | Part number is shown and matches the file name / BOM | Critical | Not reviewed
12 | Identification | Drawing number or document number is shown | Critical | Not reviewed
13 | Identification | Drawing title / part description is clear | Standard | Not reviewed
14 | Identification | Revision code and revision date are shown | Critical | Not reviewed
15 | Identification | Units are identified | Critical | Not reviewed
16 | Identification | Scale is identified or marked NTS | Standard | Not reviewed
18 | Identification | Drawing approval / release status is shown | Standard | Not reviewed
19 | Material & Finish | Material grade and applicable standard are specified | Critical | Not reviewed
20 | Material & Finish | Raw material form is clear: sheet, plate, tube, bar, casting, etc. | Standard | Not reviewed
21 | Material & Finish | Sheet thickness / tube wall / stock size is specified | Critical | Not reviewed
27 | Dimensions & Geometry | Overall length, width and height are fully defined | Critical | Not reviewed
28 | Dimensions & Geometry | Datum origin or dimensional reference is clear | Critical | Not reviewed
39 | Tolerances & GD&T | General dimensional tolerance standard is stated | Critical | Not reviewed
40 | Tolerances & GD&T | Critical dimensions have explicit tolerances | Critical | Not reviewed
47 | Manufacturing & Welding | Intended manufacturing process is compatible with the drawing | Standard | Not reviewed
51 | Manufacturing & Welding | Deburr and sharp-edge requirements are specified | Standard | Not reviewed
63 | Quality & Validation | Critical-to-quality characteristics are identified | Critical | Not reviewed
KingsForm Engineering Toolkit |  |  | KFR-002 ¦ Version 1.0 |  |  |  | www.kingsformmetalworks.com

## REVIEW RECORD
ENGINEERING REVIEW & APPROVAL RECORD | [5 empty] | KFR-002
Version 1.0
Use this record for internal review and release approval. Set Requirement to Not required where a department does not participate.
REVIEW STEPS |  | REQUIRED / ACTIVE |  | APPROVED |  | OPEN APPROVALS |  | APPROVAL SCORE
6 |  | 2 |  | 0 |  | 2 |  | 0%
No. | Department / Review | Requirement | Approval Status | Reviewer | Review Date | Comments / Conditions | Readiness | Signature / Initials | Next Action
1 | Engineering drawing review | Required | Not started |  |  |  | Open
2 | Purchasing / commercial package review | If applicable | Not started |  |  |  | Not active
3 | Quality requirements review | If applicable | Not started |  |  |  | Not active
4 | Production / manufacturability review | If applicable | Not started |  |  |  | Not active
5 | Project management release review | Required | Not started |  |  |  | Open
6 | Customer approval / confirmation | If applicable | Not started |  |  |  | Not active
FINAL RELEASE
Package Release Status |  |  |  |  | Release Date
Released By |  |  |  |  | Final Revision
Release Notes
KingsForm Engineering Toolkit |  |  | KFR-002 ¦ Version 1.0 |  |  |  | www.kingsformmetalworks.com

## DOCUMENT INFO
DOCUMENT INFORMATION & MASTER STYLE | [5 empty] | KFR-002
Version 1.0
This workbook uses the fixed visual system approved in KFR-001. Future changes should affect content only.
DOCUMENT CONTROL
Document ID | KFR-002 |  |  | Document Title | Project Documentation & Drawing Checklist
Series | KingsForm Engineering Toolkit |  |  | Version | 1.0
Release Date | 2026-07-16 |  |  | Status | Released
Document Owner | KingsForm Engineering |  |  | Approved By | Management
Website | www.kingsformmetalworks.com |  |  | Email | info@kingsformmetalworks.com
Master Style | KFR-001 Version 2.0 |  |  | Style Status | Locked
REVISION HISTORY
Version | Release Date | Change Description |  |  | Prepared By |  | Approved By
1.0 | 2026-07-16 | Initial release using the locked KFR-001 master workbook visual system. |  |  | KingsForm Engineering |  | Management
WORKBOOK CONTENT
COVER |  |  | Purpose, workflow, readiness principles and document control.
DASHBOARD |  |  | Weighted readiness score, risk metrics and final release checks.
PROJECT INFO |  |  | Project identity, drawing-package basis and review responsibility.
REQUIRED DOCUMENTS |  |  | File-package requirements, revision tracking and document readiness.
DRAWING REVIEW |  |  | Detailed drawing completeness review with weighted criticality.
ACTION REPORT |  |  | Automatic mirror of unresolved drawing checks with closure tracking.
REVIEW RECORD |  |  | Engineering, quality, purchasing and release approvals.
REFERENCE LISTS |  |  | Controlled dropdown values used throughout the workbook.
LOCKED STYLE RULES
01 | Use the approved navy, engineering blue, orange, yellow-input and grey-calculated color system.
02 | Use Aptos for all workbook text; maintain the same title, section-bar and footer hierarchy.
03 | Keep customer-editable cells yellow and calculated status cells grey or pale blue.
04 | Use formula-driven dashboards, dropdown validation and conditional formatting in every workbook.
05 | Do not redesign subsequent files. Replace content and logic only.
KingsForm Engineering Toolkit |  |  | KFR-002 ¦ Version 1.0 |  |  | www.kingsformmetalworks.com

## REFERENCE LISTS
Yes / No / TBD | Document Requirement | Document Status | Review Requirement | Review Status | Criticality | Approval Status | Department | Package Scope | Units | File Type | Drawing Standard | Owner
Yes | Required | Attached | Required | Confirmed | Critical | Not started | Engineering | Single part | mm | PDF | ISO | Customer Engineering
No | If applicable | Will send later | If applicable | Not reviewed | Standard | In review | Purchasing | Multi-part project | inch | STEP / STP | ASME Y14.5 | Customer Purchasing
To be confirmed | Not required | Not available | Not required | Missing | Advisory | Approved | Quality | Welded assembly | Mixed / drawing-specific | IGES / IGS | DIN | Customer Quality
|  | Not required |  | Needs clarification |  | Approved with comments | Production | Mechanical assembly |  | DXF | GB / T | KingsForm Engineering
|  |  |  | Not applicable |  | Rejected / Revise | Project Management | Prototype |  | DWG | JIS | KingsForm Quality
[7 empty] | Management | Production transfer |  | XLSX / XLS | Customer standard | Project Manager
[7 empty] | Customer |  |  | Image | Not specified | To be assigned
Other